## Slide 1: C-5M Elevated Risk Flight Test CRM Lessons Learned
Wade Smith, Chief Engineer
Maj Matt Schnoor, Test Pilot
Jessica Wojtanowski, Flight Test Engineer
Mariusz Wisniewski, Flight Test Engineer
Detachment 4, 418 FLTS, AFFTC
2007 SETP FLIGHT TEST SAFETY WORKSHOP
The views expressed in this article are those
of the author and do not necessarily reflect the official policy or position of the Air Force, the Department
of Defense or the U.S. Government.

## Slide 2: PRESENTATION OVERVIEW
Reliability Enhancement & Re-engining Program (RERP) Description
Test Aircraft/Control Room/Comm Setup
RERP First Flight
Flutter Overview
Flutter Test Script
Snowbird Flutter Run
Issues
Edwards Flutter Run
Lessons Learned/Recommendations
Questions

## Slide 3: C-5M MODIFICATION
ADDITIONAL REFERENCES:
- Initial Flight Testing of the C-5M Super Galaxy, Stephen A. Knoblock, presented at the 50th SETP Symposium, September 2006, Anaheim, CA.
- C-5 Reliability Enhancement & Re-Engining Program (RERP) Initial Flight Test, Wade R. Smith, presented at the 38th SFTE International Symposium, September 2006, Reno, NV.

## Slide 4
C-5M FLIGHT DECK
Pilot
Copilot
TC
FE
Discipline Engineer or Scanner

## Slide 5
General setup:
  Test Directors communicate to the airplane
  10 discipline engineers on control room net, can also make a KIO call over radio
Emergency backup stand-alone radio available
  Used often with 100% reliability
  Handheld telephone, hard to incorporate control room headset
Echo existed due to different methods, transmit & receive
  Transmit to aircraft via radio tuned to mission frequency
  Copilot ICS box on the airplane telemetered to control room, heard by all
C-5M MISSION CONTROL ROOM
10 Discipline Engineer Stations
2 Test Director Stations

## Slide 6: COMMUNICATION ROADMAP
Mission Frequency
Common Center Frequency
Control Room
ATC
ICS in TM

## Slide 7: RERP FIRST FLIGHT
Assessed as High Risk: Chase, Min Crew, TM to Cont’l Rm
First Flight 19 Jun 06: Predicted to take 1-2 flights, 4 req’d
Primary goal: Demo aircraft flightworthiness
  System demos w/in limited envelope
  Combination of dedicated test points, functional checks

## Slide 8: RERP FIRST FLIGHT
Anomalies:
  Flaps (jammed at 100%)
  Thrust Reversers (asymmetric deployment on landing)
CRM:
  Comm
    Constant ATC comm was a nuisance
    Poor Reception
    Control Room Echoing
  Test Discipline
    Aircraft out-of-synch with control room & chase
CRM Solutions:
  Intercom TM moved from Copilot to Jump (onboard TC)
  Emphasis on developing & adhering to test script
  Applied in flutter test planning

## Slide 9: FLUTTER MANEUVER
-7.0 deg
1.6 Nz
23.4K
20.4K
~27K entry altitude, 0.84 Mach
Pilot performed Elevator, Aileron, & Rudder rap separately with 5 second intervals between each axis
22.4K
MACH
KCAS
22.4K
MACH
KCAS
402
391
.880
.869
Speed
Band
Altitude
Band
20-25 sec to complete

## Slide 10: FLUTTER TEST SCRIPT
Onboard Test Conductor (OTC): Test Card Brief
Control Room Test Director (TD): “Control Ready”
Chase: “Chase Ready”
Pilot Flying (PF): Accel to pre-dive speed
PF: “Pilot Ready”
OTC: Confirm target speeds, aircraft configuration
OTC: “Cleared to Maneuver”
PF: “Initiating Dive”
OTC: Call speeds, slow or fast
Pilot Not Flying (PNF): “In Altitude Band”, SAS OFF if required
OTC: “On Conditions”
PF: “Go”
Scanner: “Knee” (passing 22,400 ft, Mach to KCAS transition)
OTC: “Maneuver Complete, Recover”
TD: “Data in Progress”
Chase: “Clean and Dry”
TD: “Cleared to Next Card”
STANDARDIZED TERMINOLOGY
“CHECK SPEED”
“SLOW-DOWN”
“KNOCK-IT-OFF”
“ABORT”

## Slide 11: COMMUNICATION ROADMAP
Mission Frequency
Common Center Frequency
Control Room
ATC
ICS in TM
TC
CP
P

## Slide 12: SNOWBIRD FLUTTER RUN
Airspace
  Snowbird MOA in Tennessee
  MOA lateral confines very small
    On Conditions: ~.875M/500 KGS
    ~8 nm/min
    ~6.5 nm turn radius
  Not exclusive of other traffic
  ATC focus on commercial traffic
Communication
  Multiple players (test aircraft, chase, control)
  Frequency congestion (mission and ATC)
  Superfluous (script not adhered to)
    96 sec: chase “abort” call to test aircraft acknowledgement
    Flutter rap callouts

## Slide 13: PRIMARY FLIGHT DISPLAY
Airspeed
Altitude
Heading
VVI
Mach
AoA
Gnd Speed

## Slide 15: FLUTTER ISSUES
Airspace
  MOA lateral confines very small
  Not exclusive of other traffic
  ATC focus on commercial traffic, not test
Communication
  Multiple players (test aircraft, chase, control)
  Frequency congestion (mission and ATC)
  Superfluous (script not adhered to)
    96 sec: chase “abort” call to test aircraft acknowledgement

## Slide 16: EDWARDS FLUTTER RUN
EDW restricted area (R-2515)
  Lateral boundaries allowed for simpler test setup
ATC focus on test aircraft, not commercial traffic
Clearer communication, script adherence emphasized

## Slide 18: LESSONS LEARNED & RECOMMENDATIONS
Recommendations:
Closely evaluate comm setup between players
  Systems approach
Consider scripting highly complex tests
  Ensure 100% “buy-in” and adherence of script
Lessons Learned:
CRM very challenging
  Multiple players
  Test complexity
Communications frequently garbled
  Hardware
  People
Improved CRM was attained by:
  Modified ICS TM feed from CP to Jump seat – Hardware
    Partially successful
    No ICS TM feed on EDW flutter
  Implemented and adhered to script – People

## Slide 19: QUESTIONS?

## Slide 20: ELEVATED RISK TESTING PLAYERS

## Slide 22: KCAS v. Altitude
~22.4K
“Knee”

## Slide 23: CONTROL COMMUNICATION NETS
Pilot
CP
TC
FE
TD
NET 5
TC
NET 1
NET 4
Propulsion Disciplinary Engineer
Avionics Disciplinary Engineer
FQ Disciplinary Engineer
Structures Disciplinary Engineer
NET 3
NET 2
Normal Comm
Network Comm
Safety Comm
SOF